## For modules 1-4, add simpler al
Module | Task | Description | Data Structure | Assigned To | Status
Module 1: Air Traffic & Runway Control
Module 1 | Plane Database | Implement storage for active aircraft details | DMA Array | Member 1 | Pending
Module 1 | Landing Queue | Implement priority-based landing order (Emergency > Scheduled) | Priority Queue | Member 1 | Pending
Module 1 | Taxiway Map | Build network of Runways and Gates | Graph | Member 1 | Pending
Module 1 | Routing Logic | Calculate optimal path for taxiing planes | Shortest Path Algo | Member 1 | Pending
Module 1 | Command History | Implement "Undo" for ATC instructions | Stack | Member 1 | Pending
Module 1 | Active Flights | Track planes currently in motion | Linked List | Member 1 | Pending
Module 1 | Flight Log | Maintain daily flight history for review | Doubly Linked List | Member 1 | Pending
Module 1 | Flight Search | Enable fast search for flights by ID | Search Tree | Member 1 | Pending
Module 2: Passenger & Terminal Management
Module 2 | Seat Map | Create seating grid for aircraft | 2D Array | Member 2 | Pending
Module 2 | Boarding Queue | Manage line for passengers waiting at gate | Queue | Member 2 | Pending
Module 2 | Check-In Database | Store passenger info for quick lookup | Search Tree | Member 2 | Pending
Module 2 | Booking Undo | Revert seat selection actions | Stack | Member 2 | Pending
Module 2 | Terminal Map | Define connections between gates and terminals | Graph | Member 2 | Pending
Module 2 | Path Finder | Find route between terminals | Search Algorithm | Member 2 | Pending
Module 2 | Passenger Manifest | List passengers for a flight | Linked List | Member 2 | Pending
Module 2 | Travel History | Log passenger trips for easy browsing | Doubly Linked List | Member 2 | Pending
Module 2 | Organize List | Sort passenger list alphabetically | Sorting Algo | Member 2 | Pending
Module 3: Baggage Handling System (BHS)
Module 3 | Container Storage | Manage storage bins for luggage | DMA Array | Member 3 | Pending
Module 3 | Scanning Queue | Queue bags for security screening | Queue | Member 3 | Pending
Module 3 | Cargo Loading | Load bags into plane (Last In, First Out) | Stack | Member 3 | Pending
Module 3 | Priority Check | Flag high-risk bags for inspection | Priority Heap | Member 3 | Pending
Module 3 | Conveyor Network | Model belt system connections | Graph | Member 3 | Pending
Module 3 | Bag Tracer | Trace bag location in network | Search Algo | Member 3 | Pending
Module 3 | Damaged Report | Log damaged bag incidents | Linked List | Member 3 | Pending
Module 3 | Lost & Found | Registry for unclaimed items | Doubly Linked List | Member 3 | Pending
Module 3 | Weight Organizer | Sort bags by weight | Sorting Algo | Member 3 | Pending
Module 4: Ground Services & Maintenance
Module 4 | Staff Database | Store staff details and roles | DMA Array | Member 4 | Pending
Module 4 | Service Queue | Queue planes for fuel/cleaning | Queue | Member 4 | Pending
Module 4 | Roster Undo | Undo staff schedule changes | Stack | Member 4 | Pending
Module 4 | Part Search | Search inventory for spare parts | Search Tree | Member 4 | Pending
Module 4 | Service Roads | Model tarmac road network | Graph | Member 4 | Pending
Module 4 | Vehicle Routing | Calculate best routes for service trucks | Routing Algo | Member 4 | Pending
Module 4 | Task Scheduler | Order tasks based on dependencies | Dependency Algo | Member 4 | Pending
Module 4 | Service Alerts | Notify delays in service | Linked List | Member 4 | Pending
Module 4 | Maintenance Log | Track repair history | Doubly Linked List | Member 4 | Pending